- SPECIAL CONDITIONS

# CONTENTS

These conditions amplify and supplement, if necessary, the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the Articles of the General Conditions.

Article 2	Language of the Contract

2.1	The language used shall be English and Latin letter only.

Article 4	Communications

4.1	Any written communication relating to this Contract between the Contracting Authority and/or the Project Manager, on the one hand, and the Contractor on the other must state the Contract title and identification number, and must be sent by post, e-mail or by hand.

For the Contracting Authority- Project Partner:

UCH Mostar

Project Office
Kralja Tvrtka bb, 88 000 Mostar
E-mail: uredzaprojekte@skbm.ba

For the Contractor:

<Contact name
Address
E-mail>

Article 7	Supply of documents

7.7 The Contractor shall deliver all technical, regulatory and user documentation necessary for import, installation, acceptance, licensing and operation of the equipment, including manufacturer’s certificates of conformity, test reports, installation drawings, and user manuals.

7.8 All documentation shall be provided in English and in at least one official language of Bosnia and Herzegovina, in a version clearly understandable to the end-user staff. All documents must comply with the applicable regulatory and licensing requirements of Bosnia and Herzegovina.

7.9 The documentation shall include the Acceptance Testing Record, forming part of the documentation necessary for clinical licensing.

Article 8	Assistance with local regulations

8.1 The Contractor shall obtain all permits, licences and authorisations required for import, transport, possession, installation and start-up of the system up to and including the stage of acceptance testing. All related applications and regulatory communications prior to acceptance testing shall be carried out by, or on behalf of, the Contractor, in accordance with the applicable laws and regulations of Bosnia and Herzegovina.

Article 10	Origin

  - 10.1	All supplies purchased under a procurement contract, or in accordance with a grant agreement, financed under IPA III shall originate from an eligible country or from any country which is eligible under the rules of the partner or other donor or member state or determined in the constitutive act of the trust fund.All supplies under this contract may originate from any country.

Article 11	Performance guarantee

11.1     The amount of the performance guarantee shall be 5 % of the total Contract price, including any amounts stipulated in addenda to the Contract.

Article 12	Liabilities and Insurance

12.1a)

No liability / insurance measures are required.

12.1b)

No liability / insurance measures are required.

12.2. Insurance

No liability / insurance measures are required.

12.2a), paragraph 2	By derogation from Article 12.2, a), paragraph 2 of the General Conditions the Contractor does not have to provide the Contracting Authority with all cover notes and/or insurance certificates showing that the Contractor's obligations relating to insurance are fully respected.

- DDP - Delivered Duty Paid: Incoterm which imposes on the seller maximum obligations vis-à-vis transportation and loss risks and damage associated with the goods:

"the seller delivers the goods when the goods are placed at the disposal of the buyer, cleared for import on the arriving means of transport ready for unloading at the named place of destination. The seller bears all the costs and risks involved in bringing the goods to the place of destination and has an obligation to clear the goods not only for export but also for import, to pay any duty for both export and import and to carry out all customs formalities." The transfer of risks and costs occurs at the place of unloading of the goods at the agreed place of destination.

Article 13	Programme of implementation of tasks

13.1 The Contractor shall submit a detailed programme of implementation describing and sequencing at minimum 14 days after signing the contract :

(a) decommissioning and removal of existing equipment;
 (b) site preparation and infrastructure adaptation;
 (c) delivery and unloading of the new system;
 (d) installation, calibration and connection of subsystems;
 (e) acceptance testing;
 (f) commissioning of the Treatment Planning System (TPS);
 (g) user training; and
 (h) warranty and technical-support phase.

Article 18	Commencement order

18.1	The implementation of the tasks is to commence from the last signature of the Contract.

Article 19	Period of implementation of the tasks

The period of implementation of the task is 210 calendar days in total, starting from the day after the signing of the Contract by the last contracting party and ending on the day of issuance of the certificate of provisional acceptance. This implementation period includes the supply, delivery and installation of equipment within 90 calendar days and 90 for the completion of all other tasks by the tenderer, including calibration, acceptance testing and commissioning, and 30 days for the issuance of the certificate of provisional acceptance by the Contracting authority- Project partner.

The first 90 days (first phase) shall, together with supply, delivery and installation of equipment also include: :

(a) decommissioning and removal of existing equipment;

(b) site preparation and infrastructure adaptation;

(c) delivery and unloading of the new system;

(d) installation and interconnection of subsystems;

The second 90 days (second phase) shall include:

(e) calibration

(f) acceptance testing;

(g) commissioning of the Processing Planning System (TPS);

Article 24	Quality of supplies

24.1 Supplies shall conform to the manufacturer’s specifications and relevant international standards for medical linear accelerators and associated software systems.

Article 25	Inspection and testing

25.1 Inspection and testing of the supplies shall be carried out at the installation site, in the presence of the Contracting Authority’s designated representatives and a duly authorised representative of the Contractor.

25.2 Radiation-Protection Survey (RPS): Before Acceptance Test (AT), a Radiation Protection Expert appointed by the Contracting Authority shall verify that all shielding elements comply with prescribed radiation-protection requirements and that measured dose-rates meet applicable standards. The RPS report shall form part of the final acceptance dossier.

25.3 Acceptance Test (AT):

The Contractor shall perform the acceptance test of the linear accelerator and all sub-systems (including imaging, control, safety/interlock, patient-support and other manufacturer-specified components) in accordance with the manufacturer’s official acceptance-testing procedures and contractual specifications. The AT shall be conducted under the supervision of, and co-signed by, a medical physicist designated by the Contracting Authority, who shall confirm that the measured parameters conform to the manufacturer’s tolerances and to the functional requirements specified in the Contract.

25.4 Upon completion of testing, the Contractor shall prepare a written Acceptance-Testing Record in duplicate, signed by both Parties, and shall provide one complete copy, covering the accelerator and all sub-systems as specified by the manufacturer, to the Contracting Authority.
This record forms an integral part of the hand-over documentation and the basis for Provisional Acceptance.

25.5 End-to-End (E2E) Test of the Treatment Planning System:
After successful completion of the Acceptance Test, the Contracting Authority’s designated medical physicists shall perform an end-to-end test verifying the accuracy of the entire planning-to-delivery chain.
The E2E test shall be carried out in accordance with the following international standards. The E2E test report shall be appended to the acceptance dossier.

Article 26	General principles for payments

26.1	Payments shall be made in euro.

The Contractors invoices shall be issued in euro (EUR),

All amounts are to be quoted excluding VAT. The program exempts the Contract Authority-Project Partner from paying VAT, because the total value of the project from which the equipment is procured exceeds 5,000,000,00EUR. Upon awarding the Contract, the Contracting Authority - Project partner will hand over the VAT exemption certificate to the selected supplier.

Payments shall be authorised and made by University Clinical Hospital Mostar, Oncology Clinical, Bijeli Brijeg bb, 88000 Mostar

26.5	In order to obtain payments, the Contractor must forward to the authority referred to in paragraph 26.1 above:

Payment will be made by the Contracting Authority-Project partner in two phase after the completion of each of the phases as follows: .

After completion of fist phase i.e.:

(a) decommissioning and removal of existing equipment;

(b) site preparation and infrastructure adaptation;

(c) delivery and unloading of the new system;

(d) installation and interconnection of subsystems;

the Contracting Authority will pay 40% of the total value of the contract, no later than 30 days after the issuance of the partial provisional acceptance

After completion of the second phase i.e.:

(e) calibration

(f) acceptance testing;

(g) commissioning of the Processing Planning System (TPS);

, the Contracting Authority- Project partner will pay 60% of the total value of the contract, no later than 30 days after the issuance of the partial provisional acceptance

The Contracting authority-project partner will, after the completion of acceptance issue one single final provisional acceptance for the entire system to mark the commencement of warranty period.

Article 29	Delivery

29.3	The packaging shall remain the property of the Contractor subject to environmental considerations.

29.4.            Upon successful completion of acceptance testing of all system components, including end-to-end testing of the Treatment Planning System, the Contracting Authority shall assume responsibility for obtaining the clinical licence and any other authorisations necessary for the clinical use and operation of the system. The Contractor shall provide all technical and regulatory documentation required to support such applications but shall have no responsibility for the administrative or legal procedures of licence issuance beyond the acceptance testing stage

29.5/6/7

This statement shall include a detailed list of all items and components delivered, indicating for each its description and quantity, and shall correspond to the contractual scope of supply to enable verification of completeness and conformity with the Technical Specifications.

Article 31	Provisional acceptance

31.1 The Certificate of Provisional Acceptance shall be issued by the Contracting Authority after all inspection and testing activities described in Article 25 have been successfully completed, and after the Contracting Authority has received and verified:

(a) decommissioning and removal of existing equipment;
 (b) site preparation and infrastructure adaptation;
 (c) delivery and unloading of the new system;
 (d) installation and connection of subsystems;
 (e) acceptance testing;
 (f) commissioning of the Treatment Planning System (TPS);

(g) calibration

The Certificate of Provisional Acceptance shall refer to point 26.5.

Report confirming that measured results are within tolerance of the applicable standards referenced in Article 25.5.

31.2 The Certificate shall be issued using the template in Annex C11 and dated accordingly. The date of signature by the Contracting Authority shall constitute the official date of Provisional/Final Acceptance.

Article 32	Warranty obligations

32.1 The Contractor shall provide a warranty of twelve (12) months from the date of Provisional Acceptance, covering all parts, labour, software and travel costs.

32.2 The warranty shall include preventive and corrective maintenance, software updates and on-site technical support sufficient to maintain clinical operability.

Article 33	After-sales service

33.1 The Contractor shall provide user training for medical, technical and physics staff as part of the contractual obligations, ensuring independent and safe operation of the system.

33.2 After expiry of the warranty, optional service contracts may be concluded under separate agreements.

Article 40	Settlement of disputes

40.4	Any disputes arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction Municipal Court in Mostar in accordance with the national legislation of the state of the Contracting Authority

- * * *

See http://www.iccwbo.org/products-and-services/trade-facilitation/incoterms-2010/the-incoterms-rules/.

* IAEA TRS-430, Commissioning and Quality Assurance of Computerized Planning Systems for Radiation Treatment of Cancer, IAEA, Vienna, 2004.

* IAEA TECDOC-1583, Commissioning of Radiotherapy Treatment Planning Systems: Testing for Typical External Beam Treatment Techniques, IAEA, Vienna, 2008.

* AAPM TG-186, Model-Based Dose Calculation Methods in Brachytherapy Beyond the 
TG-43 Formalism, Med. Phys. 39(10), 2012.

* ESTRO Booklet No. 8, Guidelines for Quality Assurance of Brachytherapy Treatment Planning Systems, ESTRO, Brussels, 2004.